## JSON Service Estimates
Application | Service Summary | Service Detail | Priority | ETA | Developer
Applause Client APIs | Generate verification code | Phone number mode | Med | 2016-09-02
|  | Email mode | Low | 2016-09-02
| Verify Code | Phone number mode | Med | 2016-09-02
|  | Email mode | Low | 2016-09-02
| Get country list |  | Low | 2016-09-09
| Register |  | High | 2016-08-30
| Get TnC and Privacy policy text |  | Low | 2016-09-09
| Login | Username | High | 2016-08-30
|  | Facebook | Med | 2016-09-09
|  | Guest | High | DONE | Gaurav
| Fetch profiles for beacons |  | High | DONE | Gaurav
| Fetch all profiles |  | Med | DONE | Gaurav
| Fetch brand details |  | High | DONE | Gaurav
| Update interactions |  | High | 2016-09-02
| Submit feedback |  | High | DONE | Gaurav
| Get feedback history |  | Low | 2016-09-09
| Update profile |  | Low | 2016-09-02
Employee App APIs | Fetch all entities |  | High | 2016-09-02
| Search Employee for location |  |  | 2016-09-02
| Get image for employee IDs |  | Low | 2016-09-02
| Update Employee profile image |  | Low | 2016-09-02
| Register beacon |  | High | 2016-09-02
| Re-register beacon |  |  | 2016-09-02

## Portal work estimates
No | Module | Functionality | Order | Priority | Server – ETA | Server – Developer | UI – ETA | UI – Developer
1 | Customer Management | Create Customer | 1 | Highest | DONE |  | 2016-08-28
2 | Brand Management | Create Brand | 2 | Highest | DONE |  | 2016-08-28
3 | Location Management | Create Location | 3 | Highest | DONE |  | 2016-08-28
4 | Employee Management | Bulk Upload | 4 | Highest | 2016-09-02 |  | 2016-09-06
5 | Beacon Management | Assign | 5 | Highest | 2016-09-02 |  | 2016-09-06
6 | Beacon Management | Unassign | 6 | High | 2016-09-02 |  | 2016-09-06
7 | Employee Management | Create Employee | 7 | High | DONE |  | 2016-08-28
8 | Beacon Management | Assign Individual | 8 | High | 2016-09-02 |  | 2016-09-06
9 | Location Management | Delete Location | 9 | Med | 2016-09-09 |  | 2016-09-16
10 | Brand Management | Delete Brand | 10 | Med | 2016-09-09 |  | 2016-09-16
11 | Customer Management | Delete Customer | 11 | Med | 2016-09-09 |  | 2016-09-16
12 | Beacon Management | View and Search | 12 | Med | 2016-09-16 |  | 2016-09-16
13 | Brand Management | Edit Brand | 13 | Med | 2016-09-16 |  | 2016-09-16
14 | Location Management | Edit Location | 14 | Med | 2016-09-16 |  | 2016-09-16
15 | Customer Management | Edit Customer Profile | 15 | Med | 2016-09-16 |  | 2016-09-16
16 | Employee Management | Edit | 16 | Med | 2016-09-02 |  | 2016-09-16
17 | Employee Management | History | 17 | Low | 2016-09-16 |  | 2016-09-16
18 | Applause Tasks | Update Contact Details | 18 | Low | 2016-09-20 |  | 2016-09-24
19 | Applause Tasks | Update Privacy Policy | 19 | Low | 2016-09-20 |  | 2016-09-24
20 | Applause Tasks | Update Terms | 20 | Lowest | 2016-09-20 |  | 2016-09-24
21 | Applause Tasks | Update About Us | 21 | Lowest | 2016-09-20 |  | 2016-09-24
22 | Applause Tasks | Update Country List | 22 | Lowest | 2016-09-20 |  | 2016-09-24